## Dashboard
Concert for a Cure 2026 — Execution Dashboard
Live view: pulls from Weekly Tracker tab
Status Snapshot
Total tasks | 85
Done | 0
In Progress | 1
Blocked | 0
Not Started | 84
% Complete | 0%
Founder review items open | 60
Workstream Breakdown
Workstream | Total | Done | % Complete
Leadership | 3 | 0 | 0%
Fundraising | 13 | 0 | 0%
Auction | 2 | 0 | 0%
Food & Beverage | 6 | 0 | 0%
Entertainment | 5 | 0 | 0%
Tribute | 9 | 0 | 0%
Sponsors | 8 | 0 | 0%
Guest Experience | 3 | 0 | 0%
Venue | 3 | 0 | 0%
Photography | 3 | 0 | 0%
Volunteer Ops | 3 | 0 | 0%
MJFF / Kiera | 2 | 0 | 0%
Rentals | 1 | 0 | 0%
Run of Show | 3 | 0 | 0%
Setup | 4 | 0 | 0%
Execution | 11 | 0 | 0%
Logistics | 1 | 0 | 0%
Stewardship | 3 | 0 | 0%
Financials | 1 | 0 | 0%
Retrospective | 1 | 0 | 0%

## Weekly Tracker
Concert for a Cure 2026 — Weekly Execution Tracker
Event: Saturday, July 18, 2026 • 2:00–6:00 PM ET • Lakeside Home • 100 guests
Week / Target Date | Workstream | Task | Owner | Support Person | Deadline | Dependency | Status | Founder Review Needed? | Notes
T-13 / Apr 20–26 | Leadership | Lock Master Operating Plan v2 as single source of truth; distribute to all leads | Wendy | — | Apr 24 | — | In Progress | Yes | This tracker + v2 plan replaces prior versions
T-13 / Apr 20–26 | Leadership | Schedule 30-min kickoff call with each of 5 leads (Hospitality, Volunteer Ops, Fundraising, Tribute, Sponsor) | Wendy | — | Apr 26 | Plan distributed | Not Started | Yes | Walk them through their one-page brief
T-13 / Apr 20–26 | Fundraising | Call Dan Abbott at Indy Boat Co — confirm boat lot, delivery timing, Rafflebox plan, speakerphone reveal moment | Wendy + Rob | — | Apr 24 | — | Not Started | Yes | Founder-only relationship; no delegation
T-13 / Apr 20–26 | Fundraising | Open Rafflebox account; configure boat raffle + 50/50 with Indiana charitable-gaming compliance | Wendy | Rafflebox support | Apr 30 | Boat lot confirmed with Dan | Not Started | Yes | Ticket price, cap, draw date/time, T&Cs
T-13 / Apr 20–26 | Food & Beverage | Shortlist 3 caterers; send RFP (heavy passed apps + 1 chef action station, lakeside, summer) | Wendy | Hospitality Lead (advisory) | Apr 26 | — | Not Started | Yes | Wendy picks final; lead only advises on spec
T-13 / Apr 20–26 | Entertainment | Shortlist 3 bands (pop / modern country trio or quartet); request demo reels + 18 July 18 quotes | Wendy | — | Apr 26 | — | Not Started | Yes | Not a bar band; elevated lakeside energy
T-13 / Apr 20–26 | Tribute | Design brief to Sallie Lord for Butterfly Wall — scale, palette, materials, placement in program zone | Wendy | Tribute Lead | Apr 26 | — | Not Started | Yes | Architectural, not craft; photo-worthy
T-12 / Apr 27–May 3 | Fundraising | Launch boat raffle public sales (Rafflebox link in newsletter, socials, Wendy's network) | Wendy | Comms partner | May 1 | Rafflebox configured | Not Started | Yes | Pre-sell is the game; night-of is a bonus
T-12 / Apr 27–May 3 | Fundraising | Launch 50/50 pre-sales on Rafflebox (or staged opening if state requires) | Wendy | Rafflebox support | May 1 | Rafflebox configured | Not Started | Yes | Confirm IN charitable gaming compliance
T-12 / Apr 27–May 3 | Food & Beverage | Collect caterer bids; taste session bookings if needed | Wendy | Hospitality Lead | May 2 | RFPs sent | Not Started | Yes
T-12 / Apr 27–May 3 | Entertainment | Review demos; pick band; send contract | Wendy | — | May 3 | Demos received | Not Started | Yes | $750 deposit typical
T-12 / Apr 27–May 3 | Tribute | Sallie Lord design concepts reviewed; pick direction | Wendy | Tribute Lead | May 3 | Design brief sent | Not Started | Yes
T-12 / Apr 27–May 3 | Sponsors | Finalize sponsor tiers: Title, Premium, Community — list target sponsors, dollar values, moments | Wendy | Sponsor Lead | May 3 | Plan v2 read | Not Started | Yes | Moments not logos
T-11 / May 4–10 | Food & Beverage | Select caterer; sign contract; lock headcount at 100 + 10% buffer | Wendy | — | May 8 | Bids in | Not Started | Yes | Wendy signs
T-11 / May 4–10 | Food & Beverage | Beverage order: 42 bottles Veuve Clicquot Yellow Label, 2 cases backup prosecco | Wendy | Hospitality Lead | May 8 | — | Not Started | Yes | Veuve for welcome + toast only
T-11 / May 4–10 | Food & Beverage | Beverage order: premium wines (3 cs white, 2 cs rosé, 2 cs red), premium spirits, beer, NA line | Wendy | Hospitality Lead | May 8 | — | Not Started | Yes | See Plan §9 beverage spec
T-11 / May 4–10 | Entertainment | Band contract signed + deposit paid; set times locked (see ROS) | Wendy | — | May 8 | Band chosen | Not Started | Yes
T-11 / May 4–10 | Tribute | Sallie Lord — greenlight materials + begin sourcing/fabrication | Wendy | Tribute Lead | May 10 | Concept selected | Not Started | Yes
T-11 / May 4–10 | Sponsors | Send tailored sponsor decks to top prospects | Sponsor Lead | Wendy | May 10 | Tiers locked | Not Started | No | Wendy closes big ones
T-11 / May 4–10 | Fundraising | Secure auctioneer for live auction lot + paddle raise (professional, nonprofit experience) | Wendy | — | May 10 | — | Not Started | Yes
T-10 / May 11–17 | Auction | Confirm single live auction lot: Lakeside Weekend — lock dates, amenities, photo package | Wendy | — | May 15 | — | Not Started | Yes | Cut to 1 lot; fewer/better
T-10 / May 11–17 | Fundraising | Rafflebox pre-sale push #1: MJFF-aligned donor list email + social carousel | Wendy | Comms partner | May 15 | Raffle live | Not Started | No
T-10 / May 11–17 | Guest Experience | Send Save-the-Dates if not already sent; confirm guest list at 100 | Wendy | — | May 15 | — | Not Started | Yes
T-10 / May 11–17 | Venue | Tent rental booked (confirm pool deck tent + backyard program tent); lighting spec sent | Wendy | Hospitality Lead | May 17 | — | Not Started | Yes | Weather backup baked in
T-10 / May 11–17 | Photography | Hire photographer + videographer (half-day each); share 12 must-capture moments list | Wendy | — | May 17 | Plan v2 read | Not Started | Yes | No one hired yet
T-9 / May 18–24 | Sponsors | Close 2 of 3 Title-level sponsors | Wendy | Sponsor Lead | May 24 | Decks sent | Not Started | Yes
T-9 / May 18–24 | Sponsors | Close Premium tier sponsors (bar, tent, print) | Sponsor Lead | Wendy | May 24 | Decks sent | Not Started | No
T-9 / May 18–24 | Rentals | Tables, chairs, linen, glassware, bar build-out order placed | Hospitality Lead | Wendy | May 22 | Caterer signed | Not Started | No | Linen palette per Plan
T-9 / May 18–24 | Tribute | Check-in envelope design (name card + We Connect card + butterfly tag + program) — send to print | Tribute Lead | Wendy | May 24 | — | Not Started | Yes | Wendy approves final proof
T-9 / May 18–24 | MJFF / Kiera | Confirm Kiera travel, arrival time, speaking slot (4:05, 7 min), AV needs | Wendy | — | May 24 | — | Not Started | Yes | Most important external speaker
T-8 / May 25–31 | Fundraising | Raffle push #2: Dan + boat photo hero content; video w/ Dan's story | Wendy + Rob | Comms partner | May 31 | Pre-sale #1 live | Not Started | Yes
T-8 / May 25–31 | Guest Experience | RSVPs close-in tracking; chase non-responders personally | Wendy | — | May 31 | Invites sent | Not Started | Yes
T-8 / May 25–31 | Sponsors | Collect sponsor logos + bios for printed program + signage | Sponsor Lead | — | May 31 | Sponsors closed | Not Started | No
T-8 / May 25–31 | Volunteer Ops | Recruit 4 volunteers (Floor Captain, Check-In, Butterfly, Raffle); send briefs | Volunteer Ops Lead | Wendy | May 31 | — | Not Started | Yes | Only 4 total
T-8 / May 25–31 | Photography | Photographer + videographer walk-through of property (shot list + lighting windows) | Wendy | — | May 31 | Team hired | Not Started | No
T-7 / Jun 1–7 | Auction | Live auction lot collateral finalized (photo card, bid card, auctioneer script) | Wendy | Fundraising Lead | Jun 5 | Lot confirmed | Not Started | Yes
T-7 / Jun 1–7 | Fundraising | Paddle raise script drafted (emotional build → ask → release); Wendy review | Fundraising Lead | Wendy | Jun 5 | — | Not Started | Yes | See ROS 4:12–4:38
T-7 / Jun 1–7 | Tribute | Sue tribute moments drafted (toast language, Veuve cue, Sallie Lord wall signage copy) | Wendy | Tribute Lead | Jun 7 | — | Not Started | Yes | Warm and elegant, not heavy
T-7 / Jun 1–7 | Sponsors | Sponsor signage proofs reviewed + sent to print | Sponsor Lead | Wendy | Jun 7 | Logos in | Not Started | Yes
T-7 / Jun 1–7 | Venue | Parking + valet plan confirmed (lane flow, overflow, signage) | Hospitality Lead | Wendy | Jun 7 | — | Not Started | No
T-6 / Jun 8–14 | Fundraising | Raffle push #3: 50/50 tease + raffle reminder (last 40 days) | Wendy | Comms partner | Jun 12 | — | Not Started | No
T-6 / Jun 8–14 | Entertainment | Band setlist review (Sue toast transition song included); load-in logistics confirmed | Wendy | — | Jun 14 | Band booked | Not Started | Yes
T-6 / Jun 8–14 | Tribute | Butterfly Wall fabrication check-in with Sallie Lord — on track? | Wendy | Tribute Lead | Jun 14 | — | Not Started | Yes
T-6 / Jun 8–14 | Volunteer Ops | Volunteer kickoff call (all 4) — briefs walked through, Q&A, shirts sized | Volunteer Ops Lead | Wendy | Jun 14 | Recruited | Not Started | No
T-5 / Jun 15–21 | Run of Show | Draft v2 ROS converted to minute-by-minute call sheet for day-of team | Wendy | Volunteer Ops Lead | Jun 21 | — | Not Started | Yes
T-5 / Jun 15–21 | Fundraising | Paddle raise ask ladder locked ($5K / $2.5K / $1K / $500 / $250 / $100) | Wendy | Fundraising Lead | Jun 21 | Script drafted | Not Started | Yes
T-5 / Jun 15–21 | MJFF / Kiera | Send Kiera: ROS, her slot details, tone guidance, Wendy intro she'll hear | Wendy | — | Jun 21 | — | Not Started | Yes
T-5 / Jun 15–21 | Sponsors | Sponsor confirmation packets sent (event details, arrival, where to find their moment) | Sponsor Lead | — | Jun 21 | Sponsors closed | Not Started | No
T-4 / Jun 22–28 | Guest Experience | Final RSVP confirmation; share arrival instructions + parking map | Wendy | — | Jun 28 | RSVPs in | Not Started | No
T-4 / Jun 22–28 | Food & Beverage | Final headcount to caterer; menu locked; dietary notes | Wendy | Hospitality Lead | Jun 28 | RSVPs in | Not Started | Yes
T-4 / Jun 22–28 | Tribute | Envelopes + name cards printed; butterfly tags assembled (Tribute Lead + volunteer) | Tribute Lead | Butterfly volunteer | Jun 28 | Print back | Not Started | No
T-4 / Jun 22–28 | Photography | Final shot list review with photog/videog; confirm Kiera & Wendy portraits | Wendy | — | Jun 28 | — | Not Started | Yes
T-3 / Jun 29–Jul 5 | Fundraising | Raffle push #4: two-week countdown (Wendy personal message video) | Wendy | Comms partner | Jul 3 | — | Not Started | Yes
T-3 / Jun 29–Jul 5 | Run of Show | ROS tabletop walk-through with all 5 leads (verbal rehearsal, cues, handoffs) | Wendy | All leads | Jul 5 | ROS v2 drafted | Not Started | Yes
T-3 / Jun 29–Jul 5 | Sponsors | Sponsor moment placements walked with Sponsor Lead on property | Sponsor Lead | Wendy | Jul 5 | Signage back | Not Started | No
T-3 / Jun 29–Jul 5 | Entertainment | Sound check plan with band: zones (deck + basement + backyard), silence cue for 3:59 toast | Wendy | Band | Jul 5 | — | Not Started | Yes
T-2 / Jul 6–12 | Tribute | Butterfly Wall install rehearsal — Sallie Lord walk-through at property | Wendy | Tribute Lead + Sallie | Jul 11 | Fabrication done | Not Started | Yes
T-2 / Jul 6–12 | Volunteer Ops | Volunteer on-site walkthrough (positions, radios, breaks, uniforms) | Volunteer Ops Lead | Wendy | Jul 12 | — | Not Started | No
T-2 / Jul 6–12 | Fundraising | Final raffle push + last-chance 50/50 reminder; reminder: on-site sales close 4:00 PM | Wendy | Comms partner | Jul 12 | — | Not Started | No
T-2 / Jul 6–12 | Run of Show | Printed ROS call sheets + radio channel plan distributed to leads & vendors | Wendy | — | Jul 12 | ROS locked | Not Started | Yes
T-1 / Jul 13–17 | Logistics | Vendor load-in schedule confirmed (caterer, rentals, band, florist, photog) | Hospitality Lead | Wendy | Jul 15 | — | Not Started | No
T-1 / Jul 13–17 | Tribute | Butterfly Wall installed Friday afternoon (Jul 17) | Sallie Lord | Wendy + Tribute Lead | Jul 17 | Property ready | Not Started | Yes
T-1 / Jul 13–17 | Venue | Tent raised Friday Jul 17; lighting + bar build started | Hospitality Lead | Wendy | Jul 17 | Vendors scheduled | Not Started | No
T-1 / Jul 13–17 | Fundraising | Live auction lot certificate printed + frame ready for reveal moment | Fundraising Lead | Wendy | Jul 17 | Lot locked | Not Started | No
T-1 / Jul 13–17 | Leadership | Wendy day-before rest & reset; early dinner with Rob; light pre-game | Wendy | — | Jul 17 | — | Not Started | No | Founder fuel
Event Day / Jul 18 | Setup | 12:00 PM — All-hands load-in start (caterer, band, florist, rentals finalize) | Hospitality Lead | Wendy | Jul 18 12:00 | — | Not Started | Yes
Event Day / Jul 18 | Setup | 1:00 PM — Volunteer arrival; uniforms on; brief walk-through | Volunteer Ops Lead | — | Jul 18 13:00 | Load-in on track | Not Started | No
Event Day / Jul 18 | Setup | 1:30 PM — Sound check complete; all zones tested; silence cue rehearsed | Wendy | Band | Jul 18 13:30 | Setup complete | Not Started | Yes
Event Day / Jul 18 | Setup | 1:45 PM — Veuve chilled & staged for welcome pour at arrival station | Hospitality Lead | — | Jul 18 13:45 | — | Not Started | No
Event Day / Jul 18 | Execution | 2:00 PM — Doors open; guests arrive; welcome pour live | Wendy | All leads | Jul 18 14:00 | All setup done | Not Started | Yes | Showtime
Event Day / Jul 18 | Execution | 4:00 PM — Sue Toast moment (Veuve flutes distributed, music silenced) | Wendy | Band, Hospitality | Jul 18 16:00 | Program zone set | Not Started | Yes | Sacred moment
Event Day / Jul 18 | Execution | 4:05 PM — Kiera (MJFF) speaks, 7 min | Wendy | — | Jul 18 16:05 | Sue toast done | Not Started | Yes
Event Day / Jul 18 | Execution | 4:12 PM — Paddle raise (26 min) | Auctioneer | Wendy | Jul 18 16:12 | Kiera done | Not Started | Yes
Event Day / Jul 18 | Execution | 4:40 PM — Live auction: Lakeside Weekend (15 min) | Auctioneer | Wendy | Jul 18 16:40 | Paddle raise done | Not Started | Yes
Event Day / Jul 18 | Execution | 4:48 PM — Boat raffle reveal (Dan + speakerphone theater, 12 min) | Wendy + Rob + Dan | — | Jul 18 16:48 | Auction done | Not Started | Yes | Signature moment
Event Day / Jul 18 | Execution | 5:02 PM — 50/50 reveal (1 min) | Wendy | Rob | Jul 18 17:02 | Raffle done | Not Started | No
Event Day / Jul 18 | Execution | 5:05 PM — Band resumes; bar shifts to deck + backyard; dance floor opens | Band | Hospitality Lead | Jul 18 17:05 | Program done | Not Started | No
Event Day / Jul 18 | Execution | 6:00 PM — Send-off: final song, butterfly wall photos, thank-you moment | Wendy | All leads | Jul 18 18:00 | — | Not Started | Yes
Event Day / Jul 18 | Execution | 6:00–7:00 PM — Vendor teardown; volunteer sweep; leftovers managed | Hospitality Lead | Volunteers | Jul 18 19:00 | Guests depart | Not Started | No
Event Day / Jul 18 | Execution | 8:00 PM — Wendy sends thank-you text blast to top donors | Wendy | — | Jul 18 20:00 | Event closed | Not Started | Yes
Post-Event / Jul 19–26 | Stewardship | Personal thank-you notes to top 25 donors + all sponsors | Wendy | — | Jul 26 | Event done | Not Started | Yes
Post-Event / Jul 19–26 | Stewardship | Photographer & videographer deliverables received + reviewed | Wendy | — | Jul 26 | — | Not Started | No
Post-Event / Jul 19–26 | Stewardship | Impact recap email to full guest list (photos, amount raised, gratitude) | Wendy | Comms partner | Jul 26 | Final total | Not Started | Yes
Post-Event / Jul 19–26 | Financials | Reconcile raffle, 50/50, paddle raise, auction, sponsor payments; transfer to MJFF | Wendy | — | Jul 31 | All pledges in | Not Started | Yes
Post-Event / Jul 19–26 | Retrospective | Debrief call with 5 leads: what worked, what to keep, what to change for 2027 | Wendy | All leads | Aug 7 | — | Not Started | Yes

## Founder-Only Decisions
Founder-Only Decisions — Wendy Owns These
Decisions that cannot be delegated — tone, money, relationships, Sue's memory
Decision | Why Founder-Only | Target Date | Status | Notes
Caterer selection | Food is the guest-experience backbone; Wendy's taste, Sue's legacy | May 8 | Not Started | Hospitality Lead advises only
Band selection | Tone of entire event — pop/modern country, not bar band | May 3 | Not Started
Boat raffle partnership w/ Dan Abbott | Personal relationship + Rob's; Indy Boat Co is the marquee lot | Apr 24 (kickoff) | Not Started | Wendy + Rob own; no delegation
Butterfly Wall design direction (Sallie Lord) | Honors Sue; architectural statement, not craft | Apr 26 brief / May 3 direction | Not Started
Sue tribute language (toast, Veuve cue, signage copy) | Sacred, emotional; only Wendy's voice | Jun 7 | Not Started
Live auction lot — Lakeside Weekend confirmation | Single marquee lot; fewer/better | May 15 | Not Started
Paddle raise ask ladder ($5K to $100) | Fundraising math; donor psychology | Jun 21 | Not Started
Title-tier sponsor partners (top 2–3) | Strategic relationship | May 24 | Not Started | Lead can close premium + community
Kiera (MJFF) speaking slot & tone brief | Credibility anchor; 4:05 slot | Jun 21 | Not Started
Guest list & hospitality tone (tight, elevated, warm) | Curated not broad | May 15 | Not Started
Photographer + videographer hire | Memory capture; no one hired yet | May 17 | Not Started
Beverage order (Veuve + premium program) | Veuve is Sue's — cannot be wrong | May 8 | Not Started | 42 bottles + prosecco backup
Any last-minute scope change or cut | Protects the Sue Test | Ongoing | Not Started

## Delegate Now
Delegate Now — Tasks to Hand Off This Week
What to move off Wendy's plate immediately to free up founder attention
Task | Delegate To | Briefing Needed | Deadline | Status | Notes
Lead caterer RFP logistics (emails, quote collection, comparison spreadsheet) | Hospitality Lead | Spec sheet + 3 caterer shortlist | Apr 30 | Not Started | Wendy picks final
Sponsor prospect outreach (Premium + Community tiers) | Sponsor Lead | Deck + tier list + moment map | May 3 start | Not Started | Wendy closes Title tier only
Volunteer recruitment (4 volunteers) | Volunteer Ops Lead | 4 role briefs from Plan v2 | May 31 | Not Started
Butterfly Wall fabrication logistics (after concept approved) | Tribute Lead w/ Sallie Lord | Wendy's design direction + timeline | Jun 14 check-in | Not Started
Rentals order (tables, chairs, linen, glassware, bar build) | Hospitality Lead | Guest count + aesthetic palette | May 22 | Not Started
Signage & print coordination (programs, bar menus, sponsor boards) | Sponsor Lead + Tribute Lead | Design system + sponsor logos | Jun 7 | Not Started | Wendy approves proofs
Volunteer walkthrough + on-site briefing | Volunteer Ops Lead | ROS + radio plan | Jul 12 | Not Started
Vendor load-in schedule | Hospitality Lead | Final vendor list + timing | Jul 15 | Not Started
Raffle + 50/50 comms push copy (Wendy voice notes, lead writes) | Comms partner | Tone + facts brief | Ongoing | Not Started | Wendy approves each send
Parking + valet logistics | Hospitality Lead | Neighborhood map + overflow plan | Jun 7 | Not Started
Program printing + assembly (envelopes, name cards, butterfly tags) | Tribute Lead + volunteer | Proofs approved | Jun 28 | Not Started

## Vendor-Owned
Vendor-Owned Responsibilities
Professional vendors own execution; Wendy sets vision, approves proofs, signs contracts
Vendor | Owns | Contract Signed By | Fee / Budget | Contact | Notes
Caterer (TBD) | Menu design, passed apps, action station, kitchen run, service staff, clean-up | May 8 | TBD | TBD | Wendy picks
Band (TBD — pop/modern country) | Live music afternoon + cocktail + post-program; PA, zones, silence cue | May 3 | ~$3,500–5,500 | TBD | Trio or quartet
Tent + rentals | Tent raising, sides, lighting, tables, chairs, linen, glassware | May 17 | TBD | TBD | Weather backup
Florist | Arrangements for program zone, bar, butterfly wall anchor, send-off | Jun 1 | TBD | TBD | Palette per Plan
Photographer | Half-day coverage, 12 must-capture moments, portraits | May 17 | ~$1,500–2,500 | TBD | None hired yet
Videographer | Half-day coverage, highlight reel (2–3 min), Wendy thank-you cut | May 17 | ~$1,500–2,500 | TBD | None hired yet
Auctioneer | Live auction lot + paddle raise; pro nonprofit experience | May 10 | TBD (some comp) | TBD
Sallie Lord (creative lead) | Butterfly Wall design + install; tribute staging; aesthetic direction | Relationship-based | In-kind or fee | Direct | Creative partner, not vendor
Rafflebox | Boat raffle + 50/50 platform; RNG draw; compliance support | Apr 30 | % fee | Rafflebox account | IN charitable gaming
Indy Boat Co (Dan Abbott) | Boat donation, pickup logistics, speakerphone reveal moment | Apr 24 (verbal) | In-kind | Dan direct | Wendy + Rob own
Valet / parking | Lane direction, parking flow, overflow lot, signage | Jun 7 | TBD | TBD
Print shop | Envelopes, name cards, butterfly tags, signage, sponsor boards | Jun 7 | TBD | TBD
MJFF (Kiera) | Credibility anchor speaker, $2,500 event-experience contribution | Already confirmed | In-kind + $2,500 | Kiera direct